## Tickets
Ticket ID | Title | Description | What To Do (Acceptance Criteria) | Component | Plan | Priority | Phase | Est. Effort (hrs) | Dependencies | Status
OG-001 | GCP project & billing setup | Create the Google Cloud project OffGrid will run in and enable required APIs. | Create project; enable billing; enable Vertex AI API, Cloud Run API, Firestore API. | Infra | Both | P0 | Phase 0 – Setup | 1 |  | To Do
OG-002 | Firebase project init | Link a Firebase project to the GCP project for Hosting, Firestore, and Auth. | Run firebase init; enable Hosting, Firestore, Auth in the console. | Infra | Both | P0 | Phase 0 – Setup | 1 | OG-001 | To Do
OG-003 | Firestore schema setup | Create the Firestore collections used by the shared event schema. | Create collections: sessions, catalog, events, insights, matching the ER diagram in flow_diagram.md. | Infra / Data | Both | P0 | Phase 0 – Setup | 2 | OG-002 | To Do
OG-004 | Cloud Run service skeleton | Deploy a minimal FastAPI service to Cloud Run to validate the deploy pipeline before agent code exists. | Deploy 'hello world' endpoint; confirm public URL responds. | Infra | Both | P0 | Phase 0 – Setup | 2 | OG-001 | To Do
OG-005 | Vertex AI Gemini access test | Confirm service-account auth to Gemini works end to end before building on top of it. | Call Gemini Flash from a local script; confirm a response is returned. | Infra | Both | P0 | Phase 0 – Setup | 1 | OG-001 | To Do
OG-006 | Seed product catalog | Build the demo catalog with realistic SKUs. | Pull 300–500 SKUs (e.g. Kaggle Fashion Product Images); normalize into catalog schema (sku_id, name, category, price, stock, return_rate). | Data | Both | P0 | Phase 1 – Data prep | 4 | OG-003 | To Do
OG-007 | Generate catalog embeddings | Create the vectors Discovery will search against. | Run Gemini embeddings over each SKU's name + description; store as the catalog's vector field/index. | Data | Both | P0 | Phase 1 – Data prep | 3 | OG-006 | To Do
OG-008 | Generate synthetic shopper queries | Build a realistic query set including failure cases, so Discovery is tested against real-shaped input. | Use Gemini to generate ~50 queries spanning matched, vague, misspelled, and zero-result cases. | Data | Both | P0 | Phase 1 – Data prep | 2 | OG-006 | To Do
OG-009 | Assign SKU return rates | Give Fit-Check something real to trigger on. | Assign realistic return_rate values per category (apparel/footwear higher than average). | Data | Both | P0 | Phase 1 – Data prep | 1 | OG-006 | To Do
OG-010 | Build multi-store stock matrix | Support the Stockout Rescue scenario's local-availability check. | Synthesize a store x SKU inventory table across 3-5 fictional stores. | Data | Plan A | P1 | Phase 1 – Data prep | 3 |  | To Do
OG-011 | Source/generate return-condition photos | Give the Return Intelligence Agent something real to grade. | Collect or generate a small labeled image set: new / lightly-used / damaged. | Data | Plan A | P2 | Phase 1 – Data prep | 3 |  | To Do
OG-012 | Implement structured-intent function calling | Replace the separate Intent Agent with one Gemini Flash function-calling turn per the architecture review. | Define a function schema (category, attributes, budget, use_case); confirm Gemini reliably fills it from varied inputs. | Discovery Agent | Both | P0 | Phase 2 – Discovery | 4 | OG-005 | To Do
OG-013 | Implement vector search retrieval | Wire structured intent to the catalog. | Structured intent -> embedding -> Firestore vector search -> top-k SKUs with similarity scores. | Discovery Agent | Both | P0 | Phase 2 – Discovery | 4 | OG-007, OG-012 | To Do
OG-014 | Implement match-quality threshold & near-match fallback | Guarantee there is never a bare zero-result page. | Score >= 0.75 returns normal ranked results; below 0.75 explains the gap and shows near-matches instead. | Discovery Agent | Both | P0 | Phase 2 – Discovery | 3 | OG-013 | To Do
OG-015 | Implement grounded match explanations | Prevent the agent from describing products it didn't retrieve. | Gemini writes a one-line 'why this matches' per result using only the retrieved SKU's real attributes; add an explicit anti-hallucination instruction. | Discovery Agent | Both | P0 | Phase 2 – Discovery | 2 | OG-014 | To Do
OG-016 | Add image-query handling | Support 'find something like this' photo search. | Accept an uploaded photo; extract visual attributes via Gemini multimodal; feed into the same intent->retrieval pipeline as text. | Discovery Agent | Both | P0 | Phase 2 – Discovery | 3 | OG-012 | To Do
OG-017 | Log search/discovery events | Feed the Insight pipeline. | Every search call writes {type:'search', matched, score, sku_ids} to Firestore per the shared event schema. | Discovery Agent | Both | P0 | Phase 2 – Discovery | 2 | OG-003, OG-014 | To Do
OG-018 | Anti-hallucination test suite | Prove the grounding guardrail actually holds under pressure. | Write 10 adversarial prompts (e.g. 'recommend something you don't have'); confirm the agent only ever cites retrieved SKU IDs. | Discovery Agent | Both | P0 | Phase 2 – Discovery | 2 | OG-015 | To Do
OG-019 | Implement fit-check trigger logic | Only interrupt checkout when it's actually likely to help. | Trigger only when category is return-prone AND return_rate is above threshold; skip everything else. | Fit-Check Agent | Both | P0 | Phase 3 – Fit-Check & Insight | 2 | OG-009 | To Do
OG-020 | Generate SKU-specific clarifying question | Make the question feel specific, not like a generic form. | Gemini writes one targeted question grounded in that SKU's actual return pattern (e.g. sizing vs. compatibility). | Fit-Check Agent | Both | P0 | Phase 3 – Fit-Check & Insight | 2 | OG-019 | To Do
OG-021 | Handle shopper response & cart update | Turn the answer into an action, not just a log line. | Parse response into confirmed / size_changed / abandoned; update cart state accordingly; never block checkout. | Fit-Check Agent | Both | P0 | Phase 3 – Fit-Check & Insight | 3 | OG-020 | To Do
OG-022 | Log fit-check resolution events | Feed the flip-rate signal the Insight agent needs. | Write resolution outcome to Firestore per the shared event schema. | Fit-Check Agent | Both | P0 | Phase 3 – Fit-Check & Insight | 1 | OG-021, OG-003 | To Do
OG-023 | Implement event aggregation | Pull the raw material for insight generation. | Query Firestore for events in a given window (session-scoped for the demo; 7-day framing for production). | Insight Agent | Both | P0 | Phase 3 – Fit-Check & Insight | 2 | OG-017 | To Do
OG-024 | Implement semantic clustering | Group differently-worded queries that mean the same thing. | For demo scale, hand Gemini the batch of raw query strings and ask it to group and label clusters directly. | Insight Agent | Both | P0 | Phase 3 – Fit-Check & Insight | 3 | OG-023 | To Do
OG-025 | Implement code-based scoring | Keep every number trustworthy — computed, not inferred. | Compute occurrences, unique_shoppers, trend_pct, and revenue_at_risk in Python, never via the LLM. | Insight Agent | Both | P0 | Phase 3 – Fit-Check & Insight | 3 | OG-024 | To Do
OG-026 | Classify signal type | Distinguish 'buy more inventory' from 'fix the listing'. | Rule-based classification into stock gap / discoverability gap / sizing confusion based on cluster + score features. | Insight Agent | Both | P0 | Phase 3 – Fit-Check & Insight | 2 | OG-025 | To Do
OG-027 | Generate grounded merchant brief | Turn the scored signal into plain language a merchant can act on. | Gemini Pro writes prose strictly from the scored signal object; add a guardrail against inventing any figure. | Insight Agent | Both | P0 | Phase 3 – Fit-Check & Insight | 2 | OG-026 | To Do
OG-028 | Wire on-demand 'Generate Insights' endpoint | Make the loop visible live, not just in a nightly batch job. | API endpoint that runs the full pipeline synchronously against current demo session data. | Insight Agent | Both | P0 | Phase 3 – Fit-Check & Insight | 2 | OG-027 | To Do
OG-029 | Build shopper widget UI | Give the shopper a real surface to interact with. | Minimal embeddable widget: text input, image upload, result cards, fit-check question UI. | Frontend | Both | P0 | Phase 4 – Frontend & Deploy | 5 | OG-016, OG-021 | To Do
OG-030 | Build demo storefront page | Give the widget a believable context for the video. | Simple product-grid page hosting the widget. | Frontend | Both | P0 | Phase 4 – Frontend & Deploy | 3 | OG-029 | To Do
OG-031 | Build merchant dashboard UI | Give the business side a real surface. | Insight cards with revenue-at-risk badges and trend arrows; wire the 'Generate Insights' button. | Frontend | Both | P0 | Phase 4 – Frontend & Deploy | 4 | OG-028 | To Do
OG-032 | Deploy frontend to Firebase Hosting | Prove the whole thing works live, not just locally. | Publish storefront + dashboard; confirm live URLs work end-to-end against the Cloud Run API. | Frontend / Infra | Both | P0 | Phase 4 – Frontend & Deploy | 2 | OG-030, OG-031, OG-004 | To Do
OG-048 | Iterative refinement | Let a shopper narrow results conversationally instead of restarting the search each time. | Maintain conversation context across turns; extend the existing function-calling schema so a follow-up like 'show me cheaper' or 'something bolder' modifies the current filters/results instead of triggering a fresh search. | Discovery Agent | Plan A | P1 | Phase 5A – Feature extensions (Plan A) | 3 | OG-012, OG-014 | To Do
OG-049 | Multilingual & voice-first search | Let a shopper search by voice or in their own language. | Add a voice-transcription input path; let Gemini handle translation + intent extraction natively (no separate translation step); test with at least 2 non-English languages. | Discovery Agent | Plan A | P1 | Phase 5A – Feature extensions (Plan A) | 4 | OG-012, OG-016 | To Do
OG-050 | Post-purchase fit follow-up | Extend return-prevention past checkout using data already being logged. | After a fit-check-flagged purchase, trigger one personalized follow-up (email/notification stub for the demo) referencing the specific fit-check resolution logged for that order. | Fit-Check Agent | Plan A | P1 | Phase 5A – Feature extensions (Plan A) | 2 | OG-022 | To Do
OG-051 | Ask-your-data merchant chat | Turn the dashboard from static cards into something a merchant can interrogate live. | Define query functions (get_events_by_filter, get_signal_by_type, etc.); wire a chat UI into the merchant dashboard; ground every answer in function results, never an invented number, reusing the existing Insight-agent guardrail pattern. | Insight Agent | Plan A | P1 | Phase 5A – Feature extensions (Plan A) | 5 | OG-025, OG-027, OG-031 | To Do
OG-052 | Discoverability vs. stock vs. price-gap signal | Add a fourth signal type so a good-match-but-no-conversion case isn't miscategorized as a stock gap. | Extend the existing classify_signal_type logic (OG-026) with a branch that uses conversion-vs-match-score data to flag a pricing gap. | Insight Agent | Plan A | P1 | Phase 5A – Feature extensions (Plan A) | 2 | OG-026 | To Do
OG-053 | Restock-by-date urgency | Turn a flat 'restock' flag into an estimated deadline. | Use the existing trend_pct and occurrence rate to estimate days-until-stockout; surface it in the generated merchant brief. | Insight Agent | Plan A | P1 | Phase 5A – Feature extensions (Plan A) | 1.5 | OG-025 | To Do
OG-033 | Implement stockout detection | Detect the trigger condition for Rescue Mode. | Check requested SKU's stock == 0 at the shopper's local store before returning normal results. | Discovery / Rescue | Plan A | P1 | Phase 5B – New scenarios (Plan A) | 2 | OG-010 | To Do
OG-034 | Implement substitute ranking | Find a real alternative, not a random one. | Rank alternative in-stock SKUs by intent-match score. | Discovery / Rescue | Plan A | P1 | Phase 5B – New scenarios (Plan A) | 3 | OG-033 | To Do
OG-035 | Generate plain-language trade-off explanation | Make the substitute recommendation feel honest, not pushy. | Gemini explains the price/timing trade-off grounded only in the real substitute SKU's data. | Discovery / Rescue | Plan A | P1 | Phase 5B – New scenarios (Plan A) | 2 | OG-034 | To Do
OG-036 | Log rescue outcome | Feed the Insight agent with rescue-specific signal. | Log substitute_accepted / rescue_declined / stockout_lost events. | Discovery / Rescue | Plan A | P1 | Phase 5B – New scenarios (Plan A) | 1 | OG-035 | To Do
OG-037 | Implement condition grading from photo | Build the part of Return Intelligence that's actually feasible from an image. | Gemini Flash Vision call classifies new / lightly-used / damaged from an uploaded return photo. | Return Agent | Plan A | P2 | Phase 5B – New scenarios (Plan A) | 3 | OG-011 | To Do
OG-038 | Implement code-based return-risk scoring | Fix the review finding: fraud signals come from order history, not the photo. | Compute return-risk features (return frequency, multi-size ordering pattern) from order history in code, separate from the photo-based condition signal. | Return Agent | Plan A | P2 | Phase 5B – New scenarios (Plan A) | 4 | OG-006 | To Do
OG-039 | Add human-in-the-loop confirmation UI | Fix the review finding: disposition must be a recommendation, not an automatic write. | Associate PWA shows the disposition recommendation as a suggestion the associate must confirm before it's applied. | Return Agent / Frontend | Plan A | P2 | Phase 5B – New scenarios (Plan A) | 3 | OG-037, OG-038 | To Do
OG-040 | Fix duplicate Mermaid node ID | Diagram bug fix flagged in review. | Rename the outcome node 'S3' (RESTOCK) in flow_diagram.md Scenario 3 so it no longer collides with the start node 'S3'. | Docs | Both | P0 | Phase 1 – Data prep | 0.5 |  | To Do
OG-041 | Rewrite Scenario 3 fraud claim | Doc fix flagged in review; only relevant if Return Intelligence is being built. | Update solution.md to separate photo-based condition grading from code-based return-risk scoring; remove the 'fraud signals from photo' claim. | Docs | Plan A | P1 | Phase 1 – Data prep | 1 |  | To Do
OG-042 | Replace leftover filename reference | Cosmetic fix flagged in review. | Rename embed/omnirerescue.js to match the OffGrid product name in architecture.md. | Docs | Both | P2 | Phase 1 – Data prep | 0.25 |  | To Do
OG-043 | Draft pitch deck (PDF) | Build the mandatory proposal document. | Problem, solution, architecture, live screenshots, judging-criteria alignment, honest scope/roadmap slide. | Submission | Both | P0 | Phase 6 – Submission | 5 | OG-032 | To Do
OG-044 | Write & record 3-minute demo video | Build the mandatory video. | Script, record, and edit per the two-live-scenario + freeze-frame plan from the review. | Submission | Both | P0 | Phase 6 – Submission | 5 | OG-032 | To Do
OG-045 | Finalize architecture diagram for deck | Give judges a clean, honest picture of what's live vs. planned. | Export a judge-facing version of the architecture diagram, labeled with P0 vs. P1/P2 scope. | Submission | Both | P0 | Phase 6 – Submission | 2 | OG-040 | To Do
OG-046 | Repo README & category statement | Satisfy the 'clearly identify your category' requirement. | Write setup instructions; explicitly state the chosen category (Retail & Commerce). | Submission | Both | P0 | Phase 6 – Submission | 1 |  | To Do
OG-047 | End-to-end deployment verification | Final safety check before the deadline. | Full run-through on the deployed (not local) URLs immediately before submission. | Submission | Both | P0 | Phase 6 – Submission | 2 | OG-032, OG-043, OG-044 | To Do

## Summary
OffGrid AI — Ticket Backlog Summary
Total tickets | 53
P0 tickets | 36
P1 tickets | 12
P2 tickets | 5
Plan B (lean) scope — ticket count | 37
Plan B (lean) scope — total effort (hrs) | 88.75
Plan A stretch-only — ticket count | 16
Plan A stretch-only — total effort (hrs) | 42.5
Plan A full scope — total effort (hrs) | 131.25